
(PAC) Public Art Committee Meeting Minutes
 
The (PAC) Public Art Committee met on, October 2, 2026 at 10:00AM at the Rommel Center for Entrepreneurship -212 W Main St, Suite 205, Salisbury, MD 21801
In Attendance:
Chair Susan Holt, Vice-Chair Brandon Bell (via phone), Secretary Nancy Mitchell, Helene English, Max Verbits, Alena Wright, Bill Wolff, Scott Roberts, Director of the Arts Business and Culture Department, and Caroline O’Hare, Events and Culture Manager of the Arts Business and Culture Department. KT Tuminello (observing), Christine Weston (observing)

Opening: 
· Meeting called to order at 10:11AM 
· September Meeting Minutes--approved  
Old Business:
The committee voted to recommend the following site locations in order of preference to the City of Salisbury for the Sculpture Walk Project for 2027:
1.The land along West Market Street between Circle Avenue and the Friendship Bridge.
2.The Labyrinth behind City Headquarters to the river.
3.The Kayak Launch.
4.Flanking the Lot 16 Bridge to the Amphitheater.
The Committee voted not to seek outside funding for the 2027 Sculpture Walk.
The Committee voted to revise the budget on the agenda to the following, using only the Salisbury Art Prize 2027 funds of $16,000: 
	Artist’s honorarium:   $3,500 x 3					10,500
	Plinths: $1,000 x 3                    	   				  	  3,000
	Installation:			   	   				  1,000
	Unveiling				    				  1,000
	Promotion				        				     500
	Total:					    				16,000	

The Committee voted to table discussion of the 2028 Salisbury Prize, including Programming, outside funding, and to focus on completing the Sculpture Walk 2027 project.

The Committee revised the agenda calendar for the Sculpture Walk Project to the following:	
October 30th: 	
· Approval of “Vision” or Proposal by the City.
· November 30: Begin construction of plinths. Send out a call to Artists for Submissions.
· May 15: Deadline for submissions
· Friday, June 4, 2027: PAC meeting: Selection of sculptures
· Thursday, September 16, 2027: Installation and unveiling.

Important Note: At the end of the meeting, Chair Holt said Derek Jarmon had asked for a contingency Plan B if the Sculpture Walk was not approved by the city, and because time had run out, the committee would have to table it until the next meeting.
However, the Committee approved Plan B at the September 4, 2026, meeting; the minutes of which were approved, so the topic should not appear on the November 6, 2026, agenda.
New Business: 
· None discussed 
Action Items before next meeting:
· Chair Susan Holt will send the revised Vision/Proposal to the City to be approved by October 30, 2026
· Bill Wolff will write the call for submissions for the 2027 Salisbury Prize.
The meeting was adjourned at 11:11 AM
Next meeting: 10:00 AM, November 6, 2026
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